## Sheet1
Principal Objectives 2023-2028
Achieve Degree Awarding Powers
Achieve Excellent Student Outcomes
Achieve Growth
2023-2024
Item | DEPT | Action | Deadline | Reporting C’ttee | Lead | Success Indicators - What actions will mean this is completed | KPI Review Frequency
1.1 | Teaching & Learning Strategy | DAPS | Sept 2024 | QAAC | HoS | Successful submission and quality assurance visit leading to approval | Termly
1.2 | Teaching & Learning Strategy | Strengthen operational protocols; | Sept 2024 | QAAC | HoS | All Timetables & module guides published before start of term; 100% of student work returned on time | Termly
1.3 | Teaching & Learning Strategy | Enhance CCI (Continuous Course Improvement) process; | 2024-09-01 | QAAC | HoS | 100% of issues raised are actioned and resolved by next iteration of module; sufficient opportunities exist to enable staff to reflect in accelerated cycle | Termly
1.4 | Teaching & Learning Strategy | Develop our Course Review and New Programme commissioning and Development processes; | 2024-07-01 | QAAC | HoS | New process developed and 3x short course & 1 new MA/BA are identified for further initial development | Termly
1.5 | Teaching & Learning Strategy | Develop market-awareness of our HE and Short courses offer in relation to competitiors & LLE | 2024-07-01 | QAAC | HoS | Market sector-leaders and three closest competitors identified in terms of market similarities/geographical reach and size | Termly
2.1 | Student Experience | Improve Feedback rates | 2024-12-01 | SEC | TLSM | >75% feedback rates for student experience and academic surveys | Termly
2.2 | Student Experience | More formal process for acting on feedback | 2024-04-01 | SEC | SS Team | >3 you said, we did based on each set of termly feedback | Termly
2.3 | Student Experience | Set internal and external feedback metrics - benchmarking | 2024-06-01 | SEC | TLSM | Decide on 3 key internal and 3 key external metrics for judging student experience - and set targets | Monthly/Termly
2.4 | Student Experience | Act within budget each month | 2024-09-01 | SEC | TLSM | Within monthly budget | Monthly
2.5 | Student Experience | Networking opportunities | 2024-04-01 | SEC | SSC | At least one networking event hosted per term with other IHE providers | Termly
2.6 | Student Experience | Social opportunities | 2024-04-01 | SEC | SSC | At least one social event per term | Termly
2.7 | Student Experience | Social opportunities | 2024-04-01 | SEC | SSC | At least one club event per week/trip | Weekly
2.8 | Student Experience | Career development opportunities | 2024-04-01 | SEC | SSC | At least one career-based workshop/talk per month | Monthly
2.9 | Student Experience | Life skill | 2024-04-01 | SEC | SSC | At least one industry/skill-based workshop/talk per month | Monthly
2.1 | Student Experience | Retention rates - identify current and pathway to 90% across all - do we know what effects? | 2024-09-01 | SEC | TLSM | Improve continuation rates to: BA: XX% MASW: XX% Improve completion rates to: BAIF: XX% BA: XX% MASW: XX% MAFM: XX% | Termly
2.11 | Student Experience | - Alumni - create/improve links and information gathering - process for ensuring we keep in touch and know their outcomes | 2024-12-01 | SEC | MKT | At least one alumni event per year | Annually
2.12 | Student Experience | - Identify alumni timeline - ie what outcomes are 18 months from graduating | 2024-12-01 | SEC | SS Team | Record of XX% of alumni outcomes 18 months after graduating | Monthly/Annually
3.1 | People | Increase median LoS | 2024-12-01 | POC | HoO | Median LoS does not decrease per month | Monthly
3.2 | People | All staff >Xhr CPD | 2024-12-01 | POC | HoO | All staff >Xhr CPD per annum | Monthly/Annually
3.3 | People | Av CPD X hours | 2024-12-01 | POC | HoO | Av CPD X hours per annum | Monthly/Annually
3.5 | People | Metrics for place to work and develop | 2024-04-01 | POC | HoO | All staff have review and set >/= 3 development goals | Annually
3.6 | People | Identify culture / dna of org | 2024-03-01 | POC | HoO | Identify our key 3-5 values and the associated trademark behaviours | Annually
3.7 | People | Establish POC and it’s role/aim | 2024-01-01 | POC | HoO | Monthly POC meetings | Monthly
3.8 | People | Set values we hire on | 2024-02-01 | POC | HoO | All new staff hires scored on value fit and job-related competencies | Annually
3.9 | People | Standardise hiring process | 2024-02-01 | POC | HoO | Consistent process for hiring accross all departments and levels | Annually
3.1 | People | Standardise leaving process | 2024-02-01 | POC | HoO | Consistent process for offboarding accross all departments and levels | Annually
3.11 | People | Staff socialising | 2024-04-01 | POC | HoO | 1 staff social event per term | Termly
4.1 | Outreach & Community Engagement | Assessment of performance | 2024-04-01 | APC | APC/SARM | -Design and complete an Equal opportunities risk register -Identify which risks to Equality of opportunity are having the largest impact at CFS | Termly
4.2 | Outreach & Community Engagement | Strategic aims, objectives and targets | 2024-05-01 | APC | APC/SARM | -Set overall objectives for APP based on identified risks | Termly
4.3 | Outreach & Community Engagement | Strategic measures: providers’ approach to delivery of strategic aims and objectives | 2024-05-01 | APC | APC/SARM | -Decide activities and measure that will make up the intervention strategy -Collate evidence to inform intervention approach -Develop a theory of change underpinning each intervention strategy | Termly
4.4 | Outreach & Community Engagement | Investment | 2024-07-01 | APC | APC/SARM | To complete Fees, investments and targets’ (FIT) document | Termly
4.5 | Outreach & Community Engagement | Student Submissions/consulation | 2024-07-01 | APC | APC/SARM | Hold a focus group to consult students on the draft access and participation plan | Termly
4.6 | Outreach & Community Engagement | Mission awareness | 2024-12-01 | APC | APC/SARM | Undertake 3 Mission acitivites per term focussed on establishing CFS as South London's Film School. | Termly
4.7 | Outreach & Community Engagement | Student Engagement | 2024-12-01 | APC | APC/SARM | Student involvment in two local impact projects. | Termly
4.8 | Outreach & Community Engagement | Local Impact | 2024-12-01 | APC | APC/SARM | Host one event per term to share CFS Resources & knowledge back to the community. | Termly
4.9 | Outreach & Community Engagement | Co-community lead | 2024-07-01 | APC | APC/SARM | Develop two community projects | Termly
5.1 | Brand & Partnerships | Achieve student growth targets across academic programmes and short courses | 2024-10-01 | MRAC | MRAC | Reach student targets for 2024 /2025 entry and surpass last years course numbers. | Annually
5.2 | Brand & Partnerships | Develop the school's reputation in industry as an institution of excellence | 2024-12-01 | MRAC | MRAC | - Increase enquiries & applications from lead source word of mouth/recommendation. - Improve ongoing standard of student reviews. - Enter industry awards. | Monthly
5.3 | Brand & Partnerships | Establish fundamental screen industry collaborations | 2024-12-01 | MRAC | MKT/SEC | Establish one strong industry partnership termly. | Termly
5.4 | Brand & Partnerships | Develop a presence at educational, industry branding, commercial and recruitment events | 2024-12-02 | MRAC | MRAC | Attend atleast one commercial or key educational event each term as well as ongoing school recruitment events. | Termly
5.5 | Brand & Partnerships | Build our audience across digital channels | 2024-12-03 | MRAC | MKT | An ongoing increase in engagement MOM across all key social media channels. | Monthly